## Sheet1
MDR The Hague Benchmark for FEED Projects |  |  | Average weight vs Sub Total | Average weight calculated | GID AMA Methanol Proposal (FEED, OBCE, LS EPC proposal) |  |  | Project GALP Bottom of Barrel FEED (Awarded but Terminated) |  |  | Beowulf FORECAST BUDGET (FEED + 10% OBCE + binding EPC LS) |  |  | ESN Methanol (Russian) (Proposal for FEED and EPC LS) |  |  | IGP Methanol FEED / OBCE (executed by MDR Houston)
Discipline | Description | TOTAL | Distr. Phase | Of Total | TOTAL | Distr. Phase | Of Total | TOTAL | Distr. Phase | Of Total | TOTAL | Distr. Phase | Of Total | TOTAL | Distr. Phase | Of Total | TOTAL |  | Distr. Phase | Of Total
42 | Process Design & Engineering | 1250161.7746 | 38.56% | 30.35% | 27160 | 41.51% | 29.87% | 60226 | 44.01% | 34.63% | 48586.215 | 40.54% | 30% | 28583.6445 | 41.78% | 30.62% | 11092.6094 |  | 33.94% | 17.18%
42 | HSE Design & Engineering | 165029.3646 | 5.09% | 4.006% | 2797.4286 | 4.276% | 3.077% | 6775 | 4.951% | 3.895% | 6569.8 | 5.482% | 4.057% | 3875.7484 | 5.666% | 4.152% | 202.9743 |  | 0.6211% | 0.3144%
43 | Civil & Structural Engineering & Design | 432819.158 | 13.35% | 10.51% | 7274.0993 | 11.12% | 8.001% | 13111 | 9.582% | 7.538% | 15750.9 | 13.14% | 9.727% | 7751.4968 | 11.33% | 8.304% | 4023.3366 |  | 12.31% | 6.233%
44 | Mechanical Engineering | 417036.1208 | 12.86% | 10.12% | 10445.9786 | 15.97% | 11.49% | 17400 | 12.72% | 10% | 13949.1 | 11.64% | 8.614% | 7751.4968 | 11.33% | 8.304% | 7111.9245 |  | 21.76% | 11.02%
46 | Piping Design, Engineering & Stress | 458625.0426 | 14.14% | 11.13% | 7327.8 | 11.2% | 8.06% | 16118 | 11.78% | 9.267% | 14482.761 | 12.09% | 8.944% | 9301.4968 | 13.6% | 9.964% | 2465.0759 |  | 7.543% | 3.819%
47 | Electrical Engineering & Design | 230693.1563 | 7.115% | 5.6% | 4233.84 | 6.471% | 4.657% | 7967 | 5.822% | 4.581% | 6263.2106 | 5.226% | 3.868% | 4844.6855 | 7.082% | 5.19% | 3283.7361 |  | 10.05% | 5.087%
48 | Instrument Design & Engineering | 288100.6948 | 8.885% | 6.993% | 6187.92 | 9.458% | 6.806% | 15238 | 11.14% | 8.761% | 14236.8217 | 11.88% | 8.792% | 6298.0912 | 9.207% | 6.747% | 4499.3432 |  | 13.77% | 6.97%
[6 empty] | 0% | 0% | 0 |  |  | 0
Subtotal | Design & Engineering | 3242465.3117 | 100% | 78.71% | 65427.0664 | 100% | 71.96% | 136835 | 100% | 78.67% | 119838.8083 | 100% | 74% | 68406.66 | 100% | 73.28% | 32679 |  | 100% | 50.63%
31100 | Project Management | 111505.8971 | 12.71% | 2.707% | 2198.34 | 8.624% | 2.418% | 4933 | 13.3% | 2.836% | 6145 | 14.6% | 3.795% | 2200 | 8.819% | 2.357% | 2588 |  | 8.12% | 4.009%
| HSE Management | 5026.2384 | 0.573% | 0.122% | 147.1641 | 0.5773% | 0.1619% | 0 | 0% | 0% | 200 | 0.4751% | 0.1235% | 250 | 1.002% | 0.2678% | 103 |  | 0.3232% | 0.1596%
31103 | Secretarial | 74342.0793 | 8.475% | 1.805% | 1205.0383 | 4.727% | 1.325% | 2892 | 7.797% | 1.663% | 2150 | 5.107% | 1.328% | 1250 | 5.011% | 1.339% | 88 |  | 0.2761% | 0.1363%
31300 | Total Quality Management | 29957.8446 | 3.415% | 0.7272% | 566.55 | 2.222% | 0.6231% | 1170 | 3.154% | 0.6727% | 900 | 2.138% | 0.5558% | 400 | 1.604% | 0.4285% | 475 |  | 1.49% | 0.7359%
31400 | Estimating | 76240.4121 | 8.691% | 1.851% | 3600 | 14.12% | 3.96% | 3400 | 9.167% | 1.955% | 5222 | 12.4% | 3.225% | 3000 | 12.03% | 3.214% | 5834 |  | 18.31% | 9.038%
31500 | Project Controls | 143767.4308 | 16.39% | 3.49% | 4200 | 16.48% | 4.62% | 4936 | 13.31% | 2.838% | 6230 | 14.8% | 3.847% | 3000 | 12.03% | 3.214% | 2737 |  | 8.588% | 4.24%
31700 | Project Accounting | 14568.2013 | 1.661% | 0.3536% | 541.68 | 2.125% | 0.5958% | 592 | 1.596% | 0.3404% | 725 | 1.722% | 0.4477% | 400 | 1.604% | 0.4285% | 44 |  | 0.1381% | 0.06816%
31800 | Management Support | 9613.4751 | 1.096% | 0.2334% | 147.1678 | 0.5773% | 0.1619% | 829 | 2.235% | 0.4766% | 100 | 0.2375% | 0.06175% | 120 | 0.4811% | 0.1285% |  |  | 0% | 0%
32101 | Procurement Management | 70651.1855 | 8.054% | 1.715% | 4740 | 18.59% | 5.213% | 3930 | 10.6% | 2.26% | 5540 | 13.16% | 3.421% | 3400 | 13.63% | 3.642% | 2758 |  | 8.654% | 4.273%
32102 | Purchasing | 48.9 | 0.005574% | 0.001187% |  | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 |  | 0% | 0%
32103 | Expediting | 0 | 0% | 0% |  | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 |  | 0% | 0%
32104 | Inspection | 0 | 0% | 0% |  | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 |  | 0% | 0%
32105 | Logistics | 120 | 0.01368% | 0.002913% |  | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 |  | 0% | 0%
32106 | Material Man. (incl in Procurement) | 10199 | 1.163% | 0.2476% |  | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 0 | 0% | 0% | 177 |  | 0.5554% | 0.2742%
34100 | Home Office Construction/Commissioning | 32867.6724 | 3.747% | 0.7978% | 1160 | 4.551% | 1.276% | 1720 | 4.637% | 0.9889% | 1950 | 4.632% | 1.204% | 1500 | 6.013% | 1.607% | 5372 |  | 16.86% | 8.322%
34200 | Subcontracting | 23271.9926 | 2.653% | 0.5649% | 1440 | 5.649% | 1.584% | 3080 | 8.304% | 1.771% | 3490 | 8.29% | 2.155% | 3000 | 12.03% | 3.214% | 2096 |  | 6.577% | 3.247%
41000 | Project Engineering Management | 182719.3697 | 20.83% | 4.435% | 3857.75 | 15.13% | 4.243% | 7796 | 21.02% | 4.482% | 5855 | 13.91% | 3.616% | 5000 | 20.04% | 5.356% | 2842 |  | 8.917% | 4.403%
49200 | Project IT | 35001.3648 | 3.99% | 0.8496% | 629.5 | 2.469% | 0.6924% | 900 | 2.427% | 0.5175% | 1190 | 2.827% | 0.7349% | 425 | 1.704% | 0.4553% | 474 |  | 1.487% | 0.7343%
49500 | Document Management | 57325.9105 | 6.535% | 1.392% | 1058.46 | 4.152% | 1.164% | 912 | 2.459% | 0.5244% | 2400 | 5.701% | 1.482% | 1000 | 4.009% | 1.071% | 1287 |  | 4.038% | 1.994%
[6 empty] | 0% | 0% | [9 empty] | 4996 | ICWA | 15.68% | 7.74%
Subtotal | Project & Operations | 877226.9739 | 100% | 21.29% | 25491.6502 | 100% | 28.04% | 37090 | 100% | 21.33% | 42097 | 100% | 26% | 24945 | 100% | 26.72% | 31871 |  | 100% | 49.37%
TOTAL | FEED | 4119692.2857 | 100% | 100% | 90918.7166 | 100% | 100% | 173925 |  | 100% | 161935.8083 |  | 100% | 93351.66 |  | 100% | 64550 |  |  | 100%
[5 empty] | Installed Pieces |  | mhr per piece | Installed Pieces |  | mhr per piece | Installed Pieces |  | mhr per piece | Installed Pieces |  | mhr per piece | Installed Pieces |  | mhr per piece
[5 empty] | 463 |  | 196.3687 | 647 |  | 268.8176 | 918 |  | 176.4007 | 394 |  | 236.9331 | 452 |  | 142.8097
[5 empty] | Unique Services |  | mhr per Service | Unique Services |  | mhr per Service | Unique Services |  | mhr per Service | Unique Services |  | mhr per Service | Unique Services |  | mhr per Service
[5 empty] | 325 |  | 279.7499 | 403 |  | 431.5757 | 619 |  | 261.6087 | 346 |  | 269.8025
[11 empty] | No scope for readiness of PO | [5 empty] | CB&I contract value |  | 7106680
[11 empty] | Modular design | 9 months | FEED |  |  |  | original contract value |  | 6646000
[11 empty] | Schedule | 10 months | OBCE
The planned schedule was eight (8) Months FEED / OBE
[17 empty] | Number of Pieces Equipment (Total): |  |  | 451
[17 empty] | Methanol Unit (each) |  |  | 151
[17 empty] | BOP | 19 per MeOH unit; 70 (common unit 1&2)
Water Treatment 5 per MeOH unit; 30 (common unit 1&2)
Methanol HT technology
A total of 32 packages were issued for equipment inquiry
Module FEED activities have been included in the Project FEED Schedule.
There were 86 pipe rack modules and 42 process modules that were identified in the FEED Modularization Study.
These modules were competitively bid under an MRQ. Various buildings will also be installed as modules.
The following were subcontracts that were competitively bid during FEED:
[17 empty] | AR-001 | Architecture Buildings
[17 empty] | CV-004 | Piling
[17 empty] | CV-005 | Permanent Fencing
[17 empty] | ME-001 | Field Fabricated Tanks
[17 empty] | MS-001 | Heavy Haul Heavy Lift
[17 empty] | MW-001 | Raw Water Intake Structure/Outfalls
[17 empty] | EW-CV-001 | Site Prep Early Works
IGPM has selected Haldor Topsøe (HT) methanol technology.
HT through IGPM will provide a complete Basic Engineering Package utilizing their technology to convert natural gas to methanol.
The Haldor Topsøe process will use auto-thermal reforming and methanol distillation technologies.
Each methanol unit is designed for a production capacity of 5,000 MTPD of grade AA methanol.

## Sheet2
| 3988 | Marine works for IGP Methanol
38.56% | 1537.6094
5.09% | 202.9743
13.35% | 532.3366
12.86% | 512.9245
14.14% | 564.0759
7.115% | 283.7361
8.885% | 354.3432
100% | 3988
| 0 | check